SECTION 012600 - CONTRACT MODIFICATION PROCEDURES

- GENERAL

      - SUMMARY

        - Section includes administrative and procedural requirements for handling and processing Contract modifications.

      - MINOR CHANGES IN THE WORK

        - Engineer will issue through Construction Manager supplemental instructions authorizing minor changes in the Work, not involving adjustment to the Contract Sum or the Contract Time, on form included in Project Manual.

      - PROPOSAL REQUESTS

        - Owner-Initiated Proposal Requests: Engineer will issue a detailed description of proposed changes in the Work that may require adjustment to the Contract Sum or the Contract Time. If necessary, the description will include supplemental or revised Drawings and Specifications.

          - Work Change Proposal Requests issued by Engineer are not instructions either to stop work in progress or to execute the proposed change.

          - Within 20 days, when not otherwise specified, after receipt of Proposal Request, submit a quotation estimating cost adjustments to the Contract Sum and the Contract Time necessary to execute the change.

            - Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made. If requested, furnish survey data to substantiate quantities.

            - Indicate applicable taxes, delivery charges, equipment rental, and amounts of trade discounts.

            - Include costs of labor and supervision directly attributable to the change.

            - Include an updated Contractor's construction schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship. Use available total float before requesting an extension of the Contract Time.

        - Contractor-Initiated Proposals: If latent or changed conditions require modifications to the Contract, Contractor may initiate a claim by submitting a request for a change to Construction Manager.

          - Include a statement outlining reasons for the change and the effect of the change on the Work. Provide a complete description of the proposed change. Indicate the effect of the proposed change on the Contract Sum and the Contract Time.

          - Include a list of quantities of products required or eliminated and unit costs, with total amount of purchases and credits to be made. If requested, furnish survey data to substantiate quantities.

          - Indicate applicable taxes, delivery charges, equipment rental, and amounts of trade discounts.

          - Include costs of labor and supervision directly attributable to the change.

          - Include an updated Contractor's construction schedule that indicates the effect of the change, including, but not limited to, changes in activity duration, start and finish times, and activity relationship. Use available total float before requesting an extension of the Contract Time.

          - Comply with requirements in Section 012500 "Substitution Procedures" if the proposed change requires substitution of one product or system for product or system specified.

      - CHANGE ORDER PROCEDURES

        - On Owner's approval of a Work Change Proposal Request, Construction Manager will issue a Change Order for signatures of Owner and Contractor on form included in Project Manual.

      - CONSTRUCTION CHANGE DIRECTIVE

        - Construction Change Directive: Construction Manager may issue a Construction Change Directive on form included in Project Manual. Construction Change Directive instructs Contractor to proceed with a change in the Work, for subsequent inclusion in a Change Order.

          - Construction Change Directive contains a complete description of change in the Work. It also designates method to be followed to determine change in the Contract Sum or the Contract Time.

        - Documentation: Maintain detailed records on a time and material basis of work required by the Construction Change Directive.

          - After completion of change, submit an itemized account and supporting data necessary to substantiate cost and time adjustments to the Contract.

      - WORK CHANGE DIRECTIVE

        - Work Change Directive: Construction Manager may issue a Work Change Directive on form included in Project Manual. Work Change Directive instructs Contractor to proceed with a change in the Work, for subsequent inclusion in a Change Order.

          - Work Change Directive contains a complete description of change in the Work. It also designates method to be followed to determine change in the Contract Sum or the Contract Time.

        - Documentation: Maintain detailed records on a time and material basis of work required by the Work Change Directive.

          - After completion of change, submit an itemized account and supporting data necessary to substantiate cost and time adjustments to the Contract.

- PRODUCTS (Not Used)

- EXECUTION (Not Used)

END OF SECTION 012600