SECTION 013100 - PROJECT MANAGEMENT AND COORDINATION

- GENERAL

      - RELATED DOCUMENTS

        - Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 01 Specification Sections, apply to this Section.

      - SUMMARY

        - Section includes administrative provisions for coordinating construction operations on Project including, but not limited to, the following:

          - General coordination procedures.

          - Coordination drawings.

          - RFIs.

          - Digital project management procedures.

          - Project meetings.

        - Related Requirements:

          - Section 017300 "Execution" for procedures for coordinating general installation and field-engineering services, including establishment of benchmarks and control points.

      - DEFINITIONS

        - RFI: Request for Information. Request from Owner, Construction Manager, Engineer, or Contractor seeking information required by or clarifications of the Contract Documents.

      - INFORMATIONAL SUBMITTALS

        - Subcontract List: Prepare a written summary identifying individuals or firms proposed for each portion of the Work, including those who are to furnish products or equipment fabricated to a special design. Include the following information in tabular form:

          - Name, address, telephone number, and email address of entity performing subcontract or supplying products.

          - Number and title of related Specification Section(s) covered by subcontract.

          - Drawing number and detail references, as appropriate, covered by subcontract.

      - GENERAL COORDINATION PROCEDURES

        - Coordination: Coordinate construction operations included in different Sections of the Specifications to ensure efficient and orderly installation of each part of the Work. Coordinate construction operations included in different Sections that depend on each other for proper installation, connection, and operation.

          - Schedule construction operations in sequence required to obtain the best results where installation of one part of the Work depends on installation of other components, before or after its own installation.

          - Coordinate installation of different components to ensure maximum performance and accessibility for required maintenance, service, and repair.

          - Make adequate provisions to accommodate items scheduled for later installation.

        - Administrative Procedures: Coordinate scheduling and timing of required administrative procedures with other construction activities to avoid conflicts and to ensure orderly progress of the Work. Such administrative activities include, but are not limited to, the following:

          - Preparation of Contractor's construction schedule.

          - Preparation of the schedule of values.

          - Installation and removal of temporary facilities and controls.

          - Delivery and processing of submittals.

          - Progress meetings.

          - Preinstallation conferences.

          - Project closeout activities.

          - Startup and adjustment of systems.

      - COORDINATION DRAWINGS

        - Coordination Drawings, General: Prepare coordination drawings according to requirements in individual Sections, and additionally where installation is not completely indicated on Shop Drawings, where limited space availability necessitates coordination, or if coordination is required to facilitate integration of products and materials fabricated or installed by more than one entity.

          - Content: Project-specific information, drawn accurately to a scale large enough to indicate and resolve conflicts. Do not base coordination drawings on standard printed data. Include the following information, as applicable:

            - Indicate functional and spatial relationships of components of structural, civil, mechanical, and electrical systems.

            - Indicate dimensions shown on Drawings. Specifically note dimensions that appear to be in conflict with submitted equipment and minimum clearance requirements. Provide alternative sketches to Engineer indicating proposed resolution of such conflicts. Minor dimension changes and difficult installations will not be considered changes to the Contract.

        - Coordination Drawing Organization: Organize coordination drawings as follows:

          - Structural Penetrations: Indicate penetrations and openings required for all disciplines.

          - Review: Engineer will review coordination drawings to confirm that in general the Work is being coordinated, but not for the details of the coordination, which are Contractor's responsibility.

        - Coordination Digital Data Files: Prepare coordination digital data files according to the following requirements:

          - File Preparation Format: Same digital data software program, version, and operating system as original Drawings.

          - File Submittal Format: Submit or post coordination drawing files using format same as file preparation format.

          - Engineer will furnish Contractor one set of digital data files of Drawings for use in preparing coordination digital data files.

            - Engineer makes no representations as to the accuracy or completeness of digital data files as they relate to Drawings.

            - Digital Data Software Program: Drawings are available in AutoCAD.

      - REQUEST FOR INFORMATION (RFI)

        - General: Immediately on discovery of the need for additional information, clarification, or interpretation of the Contract Documents, Contractor shall prepare and submit an RFI in the form specified.

          - Engineer will return without response those RFIs submitted to Engineer by other entities controlled by Contractor.

          - Coordinate and submit RFIs in a prompt manner so as to avoid delays in Contractor's work or work of subcontractors.

        - Content of the RFI: Include a detailed, legible description of item needing information or interpretation and the following:

          - Project name.

          - Project number.

          - Date.

          - Name of Contractor.

          - Name of Engineer and Construction Manager.

          - RFI number, numbered sequentially.

          - RFI subject.

          - Specification Section number and title and related paragraphs, as appropriate.

          - Drawing number and detail references, as appropriate.

          - Field dimensions and conditions, as appropriate.

          - Contractor's suggested resolution. If Contractor's suggested resolution impacts the Contract Time or the Contract Sum, Contractor shall state impact in the RFI.

          - Contractor's signature.

          - Attachments: Include sketches, descriptions, measurements, photos, Product Data, Shop Drawings, coordination drawings, and other information necessary to fully describe items needing interpretation.

        - RFI Forms: Software-generated form with substantially the same content as indicated above, acceptable to Engineer.

        - Engineer's and Construction Manager's Action: Engineer and Construction Manager will review each RFI, determine action required, and respond. Allow seven working days for Engineer's response for each RFI. RFIs received by Engineer or Construction Manager after 1:00 p.m. will be considered as received the following working day.

          - The following Contractor-generated RFIs will be returned without action:

            - Requests for approval of submittals.

            - Requests for approval of substitutions.

            - Requests for approval of Contractor's means and methods.

            - Requests for coordination information already indicated in the Contract Documents.

            - Requests for adjustments in the Contract Time or the Contract Sum.

            - Requests for interpretation of Engineer's actions on submittals.

            - Incomplete RFIs or inaccurately prepared RFIs.

          - Engineer's action may include a request for additional information, in which case Engineer's time for response will date from time of receipt by Engineer or Construction Manager of additional information.

          - Engineer's action on RFIs that may result in a change to the Contract Time or the Contract Sum may be eligible for Contractor to submit Change Proposal according to Section 012600 "Contract Modification Procedures."

            - If Contractor believes the RFI response warrants change in the Contract Time or the Contract Sum, notify Engineer and Construction Manager in writing within ten days of receipt of the RFI response.

        - RFI Log: Prepare, maintain, and submit a tabular log of RFIs organized by the RFI number. Submit log weekly. Use software log that is part of web-based Project software. Software log with not less than the following:

          - Project name.

          - Name and address of Contractor.

          - Name and address of Engineer and Construction Manager.

          - RFI number including RFIs that were returned without action or withdrawn.

          - RFI description.

          - Date the RFI was submitted.

          - Date Engineer's and Construction Manager's response was received.

        - On receipt of Engineer's and Construction Manager's action, update the RFI log and immediately distribute the RFI response to affected parties. Review response and notify Engineer and Construction Manager within seven days if Contractor disagrees with response.

      - DIGITAL PROJECT MANAGEMENT PROCEDURES

        - Use of Engineer's Digital Data Files: Digital data files of Engineer's drawings in PDF format will be provided by Engineer for Contractor's use during construction.

          - Digital data files may be used by Contractor in preparing coordination drawings, Shop Drawings, and Project record Drawings.

          - Engineer makes no representations as to the accuracy or completeness of digital data files as they relate to Contract Drawings.

          - Digital Drawing Software Program: Contract Drawings are available in PDF.

          - Contractor shall execute a data licensing agreement in the form of Agreement form acceptable to Owner and Engineer.

            - Subcontractors, and other parties granted access by Contractor to Engineer's digital data files shall execute a data licensing agreement in the form of Agreement acceptable to Owner and Engineer.

        - PDF Document Preparation: Where PDFs are required to be submitted to Engineer, prepare as follows:

          - Assemble complete submittal package into a single indexed file incorporating submittal requirements of a single Specification Section and transmittal form with links enabling navigation to each item.

          - Name file with submittal number or other unique identifier, including revision identifier.

          - Certifications: Where digitally submitted certificates and certifications are required, provide a digital signature with digital certificate on where indicated.

      - PROJECT MEETINGS

        - General: Construction Manager will schedule and conduct meetings and conferences at Project site unless otherwise indicated.

        - Preconstruction Conference: Construction Manager will schedule and conduct a preconstruction conference before starting construction, at a time convenient to Owner and Engineer, but no later than fifteen days after execution of the Agreement.

          - Attendees: Authorized representatives of Owner,  Construction Manager, Engineer, and their consultants; Contractor and its superintendent; major subcontractors; suppliers; and other concerned parties shall attend the conference. Participants at the conference shall be familiar with Project and authorized to conclude matters relating to the Work.

          - Agenda: Discuss items of significance that could affect progress, including the following:

            - Responsibilities and personnel assignments.

            - Tentative construction schedule.

            - Phasing.

            - Critical work sequencing and long lead items.

            - Designation of key personnel and their duties.

            - Lines of communications.

            - Use of web-based Project software.

            - Procedures for processing field decisions and Change Orders.

            - Procedures for RFIs.

            - Procedures for testing and inspecting.

            - Procedures for processing Applications for Payment.

            - Distribution of the Contract Documents.

            - Submittal procedures.

            - Preparation of Record Documents.

            - Use of the premises and existing building.

            - Work restrictions.

            - Working hours.

            - Owner's occupancy requirements.

            - Responsibility for temporary facilities and controls.

            - Procedures for moisture and mold control.

            - Procedures for disruptions and shutdowns.

            - Construction waste management and recycling.

            - Parking availability.

            - Office, work, and storage areas.

            - Equipment deliveries and priorities.

            - First aid.

            - Security.

            - Progress cleaning.

          - Minutes: Entity responsible for conducting meeting will record and distribute meeting minutes.

        - Preinstallation Conferences: Conduct a preinstallation conference at Project site before each construction activity when required by other sections and when required for coordination with other construction.

          - Attendees: Installer and representatives of manufacturers and fabricators involved in or affected by the installation and its coordination or integration with other materials and installations that have preceded or will follow, shall attend the meeting. Advise Engineer, Construction Manager, and Owner's Commissioning Authority of scheduled meeting dates.

          - Agenda: Review progress of other construction activities and preparations for the particular activity under consideration, including requirements for the following:

            - Contract Documents.

            - Options.

            - Related RFIs.

            - Related Change Orders.

            - Purchases.

            - Deliveries.

            - Submittals.

            - Review of mockups.

            - Possible conflicts.

            - Compatibility requirements.

            - Time schedules.

            - Weather limitations.

            - Manufacturer's written instructions.

            - Warranty requirements.

            - Compatibility of materials.

            - Acceptability of substrates.

            - Temporary facilities and controls.

            - Space and access limitations.

            - Regulations of authorities having jurisdiction.

            - Testing and inspecting requirements.

            - Installation procedures.

            - Coordination with other work.

            - Required performance results.

            - Protection of adjacent work.

            - Protection of construction and personnel.

          - Record significant conference discussions, agreements, and disagreements, including required corrective measures and actions.

          - Reporting: Distribute minutes of the meeting to each party present and to other parties requiring information.

          - Do not proceed with installation if the conference cannot be successfully concluded. Initiate whatever actions are necessary to resolve impediments to performance of the Work and reconvene the conference at earliest feasible date.

        - Progress Meetings: Construction Manager will conduct progress meetings at weekly intervals.

          - Coordinate dates of meetings with preparation of payment requests.

          - Attendees: In addition to representatives of Owner,  Construction Manager, and Engineer, each contractor, subcontractor, supplier, and other entity concerned with current progress or involved in planning, coordination, or performance of future activities shall be represented at these meetings. All participants at the meeting shall be familiar with Project and authorized to conclude matters relating to the Work.

          - Agenda: Review and correct or approve minutes of previous progress meeting. Review other items of significance that could affect progress. Include topics for discussion as appropriate to status of Project.

            - Contractor's Construction Schedule: Review progress since the last meeting. Determine whether each activity is on time, ahead of schedule, or behind schedule, in relation to Contractor's construction schedule. Determine how construction behind schedule will be expedited; secure commitments from parties involved to do so. Discuss whether schedule revisions are required to ensure that current and subsequent activities will be completed within the Contract Time.

              - Review schedule for next period.

            - Review present and future needs of each entity present, including the following:

              - Interface requirements.

              - Sequence of operations.

              - Status of submittals.

              - Deliveries.

              - Off-site fabrication.

              - Access.

              - Site use.

              - Temporary facilities and controls.

              - Progress cleaning.

              - Quality and work standards.

              - Status of correction of deficient items.

              - Field observations.

              - Status of RFIs.

              - Status of Proposal Requests.

              - Pending changes.

              - Status of Change Orders.

              - Pending claims and disputes.

              - Documentation of information for payment requests.

          - Minutes: Entity responsible for conducting the meeting will record and distribute the meeting minutes to each party present and to parties requiring information.

            - Schedule Updating: Revise Contractor's construction schedule after each progress meeting where revisions to the schedule have been made or recognized. Issue revised schedule concurrently with the report of each meeting.

- PRODUCTS (Not Used)

- EXECUTION (Not Used)

END OF SECTION 013100