SECTION 013200 - CONSTRUCTION PROGRESS DOCUMENTATION

- GENERAL

      - SUMMARY

        - Section includes administrative and procedural requirements for documenting the progress of construction during performance of the Work, including the following:

          - Contractor's Construction Schedule.

          - Construction schedule updating reports.

          - Daily construction reports.

          - Site condition reports.

      - DEFINITIONS

        - Activity: A discrete part of a project that can be identified for planning, scheduling, monitoring, and controlling the construction Project. Activities included in a construction schedule consume time and resources.

          - Critical Activity: An activity on the critical path that must start and finish on the planned early start and finish times.

          - Predecessor Activity: An activity that precedes another activity in the network.

          - Successor Activity: An activity that follows another activity in the network.

        - CPM: Critical path method, which is a method of planning and scheduling a construction project where activities are arranged based on activity relationships. Network calculations determine when activities can be performed and the critical path of Project.

        - Critical Path: The longest connected chain of interdependent activities through the network schedule that establishes the minimum overall Project duration and contains no float.

        - Event: The starting or ending point of an activity.

        - Float: The measure of leeway in starting and completing an activity.

          - Float time is not for the exclusive use or benefit of either Owner or Contractor, but is a jointly owned, expiring Project resource available to both parties as needed to meet schedule milestones and Contract completion date.

          - Free float is the amount of time an activity can be delayed without adversely affecting the early start of the successor activity.

          - Total float is the measure of leeway in starting or completing an activity without adversely affecting the planned Project completion date.

      - INFORMATIONAL SUBMITTALS

        - Format for Submittals: Submit required submittals in the following format:

          - Working electronic copy of schedule file, where indicated.

          - PDF file.

        - Startup Network Diagram: Of size required to display entire network for entire construction period. Show logic ties for activities.

        - Contractor's Construction Schedule: Initial schedule, of size required to display entire schedule for entire construction period.

        - CPM Reports: Concurrent with CPM schedule, submit each of the following reports. Format for each activity in reports shall contain activity number, activity description, original duration, remaining duration, early start date, early finish date, late start date, late finish date, and total float in calendar days.

          - Activity Report: List of activities sorted by activity number and then early start date, or actual start date if known.

          - Logic Report: List of preceding and succeeding activities for each activity, sorted in ascending order by activity number and then by early start date, or actual start date if known.

          - Total Float Report: List of activities sorted in ascending order of total float.

        - Construction Schedule Updating Reports: Submit with Applications for Payment.

        - Daily Construction Reports: Submit at weekly intervals.

        - Site Condition Reports: Submit at time of discovery of differing conditions.

      - COORDINATION

        - Coordinate Contractor's Construction Schedule with the schedule of values, list of subcontracts, submittal schedule, progress reports, payment requests, and other required schedules and reports.

          - Secure time commitments for performing critical elements of the Work from entities involved.

          - Coordinate each construction activity in the network with other activities and schedule them in proper sequence.

      - CONTRACTOR'S CONSTRUCTION SCHEDULE, GENERAL

        - Computer Scheduling Software: Prepare schedules using current version of a program that has been developed specifically to manage construction schedules.

        - Time Frame: Extend schedule from date established for the Notice to Proceed to date of final completion.

          - Contract completion date shall not be changed by submission of a schedule that shows an early completion date, unless specifically authorized by Change Order.

        - Activities: Treat each major work item as a separate numbered activity for each main element of the Work. Comply with the following:

          - Activity Duration: Define activities so no activity is longer than twenty days, unless specifically allowed by Engineer.

          - Procurement Activities: Include procurement process activities for the following long lead items and major items, requiring a cycle of more than 60 days, as separate activities in schedule. Procurement cycle activities include, but are not limited to, submittals, approvals, purchasing, fabrication, and delivery.

            - Jet Filter System or approved equivalent.

            - Corrosion protection.

            - Steel fabrication.

            - Polymer injection material.

          - Submittal Review Time: Include review and resubmittal times indicated in Section 013300 "Submittal Procedures" in schedule. Coordinate submittal review times in Contractor's Construction Schedule with submittal schedule.

          - Drain System Testing Time: Include no fewer than 15 days for measurement and testing of drain system function.

          - Substantial Completion: Indicate completion in advance of date established for Substantial Completion, and allow time for Engineer's and Construction Manager's administrative procedures necessary for certification of Substantial Completion.

          - Punch List and Final Completion: Include not more than 30 days for completion of punch list items and final completion.

        - Constraints: Include constraints and work restrictions indicated in the Contract Documents and as follows in schedule, and show how the sequence of the Work is affected.

          - Phasing: Arrange list of activities on schedule by phase.

          - Owner-Furnished Products: Include a separate activity for each product. Include delivery date indicated in Section 011000 "Summary." Delivery dates indicated stipulate the earliest possible delivery date.

          - Work Restrictions: Show the effect of the following items on the schedule:

            - Coordination with existing construction.

            - Limitations of continued occupancies.

            - Uninterruptible services.

            - Partial occupancy before Substantial Completion.

            - Use-of-premises restrictions.

            - Provisions for future construction.

            - Seasonal variations.

            - Environmental control.

        - Milestones: Include milestones indicated in the Contract Documents in schedule, including, but not limited to, the Notice to Proceed, Substantial Completion, and final completion.

        - Upcoming Work Summary: Prepare summary report indicating activities scheduled to occur or commence prior to submittal of next schedule update. Summarize the following issues:

          - Unresolved issues.

          - Unanswered Requests for Information.

          - Rejected or unreturned submittals.

          - Notations on returned submittals.

          - Pending modifications affecting the Work and the Contract Time.

        - Contractor's Construction Schedule Updating: At monthly intervals, update schedule to reflect actual construction progress and activities. Issue schedule one week before each regularly scheduled progress meeting.

          - Revise schedule immediately after each meeting or other activity where revisions have been recognized or made. Issue updated schedule concurrently with the report of each such meeting.

          - Include a report with updated schedule that indicates every change, including, but not limited to, changes in logic, durations, actual starts and finishes, and activity durations.

          - As the Work progresses, indicate final completion percentage for each activity.

        - Recovery Schedule: When periodic update indicates the Work is 14 or more calendar days behind the current approved schedule, submit a separate recovery schedule indicating means by which Contractor intends to regain compliance with the schedule. Indicate changes to working hours, working days, crew sizes, equipment required to achieve compliance, and date by which recovery will be accomplished.

        - Distribution: Distribute copies of approved schedule to Engineer, Construction Manager, Owner, separate contractors, testing and inspecting agencies, and other parties identified by Contractor with a need-to-know schedule responsibility.

          - Post copies in Project meeting rooms and temporary field offices.

          - When revisions are made, distribute updated schedules to the same parties and post in the same locations. Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in performance of construction activities.

      - GANTT-CHART SCHEDULE REQUIREMENTS

        - Gantt-Chart Schedule: Submit a comprehensive, fully developed, horizontal, Gantt-chart-type, Contractor's Construction Schedule within 30 days of date established the Notice to Proceed.

        - Preparation: Indicate each significant construction activity separately. Identify first workday of each week with a continuous vertical line.

          - For construction activities that require three months or longer to complete, indicate an estimated completion percentage in 10 percent increments within time bar.

      - REPORTS

        - Daily Construction Reports: Prepare a daily construction report recording the following information concerning events at Project site:

          - List of subcontractors at Project site.

          - List of separate contractors at Project site.

          - Approximate count of personnel at Project site.

          - Equipment at Project site.

          - Material deliveries.

          - High and low temperatures and general weather conditions, including presence of rain or snow.

          - Testing and inspection.

          - Accidents.

          - Meetings and significant decisions.

          - Stoppages, delays, shortages, and losses.

          - Meter readings and similar recordings.

          - Emergency procedures.

          - Orders and requests of authorities having jurisdiction.

          - Change Orders received and implemented.

          - Construction Change Directives received and implemented.

          - Services connected and disconnected.

          - Equipment or system tests and startups.

          - Partial completions and occupancies.

          - Substantial Completions authorized.

        - Site Condition Reports: Immediately on discovery of a difference between site conditions and the Contract Documents, prepare and submit a detailed report. Submit with a Request for Information. Include a detailed description of the differing conditions, together with recommendations for changing the Contract Documents.

- PRODUCTS (Not Used)

- EXECUTION (Not Used)

END OF SECTION 013200