SECTION 017700 - CLOSEOUT PROCEDURES

- GENERAL

      - SUMMARY

        - Section includes administrative and procedural requirements for contract closeout, including, but not limited to, the following:

          - Substantial Completion procedures.

          - Final completion procedures.

          - Warranties.

          - Final cleaning.

          - Repair of the Work.

        - Related Requirements:

          - Section 017823 "Operation and Maintenance Data" for additional operation and maintenance manual requirements.

          - Section 017839 "Project Record Documents" for submitting Record Drawings, Record Specifications, and Record Product Data.

      - ACTION SUBMITTALS

        - Product Data: For each type of cleaning agent.

        - Contractor's List of Incomplete Items: Initial submittal at Substantial Completion.

        - Certified List of Incomplete Items: Final submittal at final completion.

      - CLOSEOUT SUBMITTALS

        - Certificates of Release: From authorities having jurisdiction.

        - Certificate of Insurance: For continuing coverage.

        - Field Report: For pest control inspection.

      - SUBSTANTIAL COMPLETION PROCEDURES

        - Contractor's List of Incomplete Items: Prepare and submit a list of items to be completed and corrected (Contractor's punch list), indicating the value of each item on the list and reasons why the Work is incomplete.

        - Submittals Prior to Substantial Completion: Complete the following a minimum of 10 days prior to requesting inspection for determining date of Substantial Completion. List items below that are incomplete at time of request.

          - Certificates of Release: Obtain and submit releases from authorities having jurisdiction permitting Owner unrestricted use of the Work and access to services and utilities. Include occupancy permits, operating certificates, and similar releases.

          - Submit closeout submittals specified in other Division 01 Sections, including project record documents, operation and maintenance manuals, damage or settlement surveys, property surveys, and similar final record information.

          - Submit closeout submittals specified in individual Sections, including specific warranties, workmanship bonds, maintenance service agreements, final certifications, and similar documents.

          - Submit maintenance material submittals specified in individual Sections, including tools, spare parts, extra materials, and similar items, and deliver to location designated by Construction Manager. Label with manufacturer's name and model number.

          - Submit testing, adjusting, and balancing records.

          - Submit changeover information related to Owner's occupancy, use, operation, and maintenance.

        - Procedures Prior to Substantial Completion: Complete the following a minimum of 10 days prior to requesting inspection for determining date of Substantial Completion. List items below that are incomplete at time of request.

          - Advise Owner of pending insurance changeover requirements.

          - Make final changeover of permanent locks and deliver keys to Owner. Advise Owner's personnel of changeover in security provisions.

          - Complete startup and testing of systems and equipment.

          - Perform preventive maintenance on equipment used prior to Substantial Completion.

          - Instruct Owner's personnel in operation, adjustment, and maintenance of products, equipment, and systems.

          - Advise Owner of changeover in utility services.

          - Participate with Owner in conducting inspection and walkthrough with local emergency responders.

          - Terminate and remove temporary facilities from Project site, along with mockups, construction tools, and similar elements.

          - Complete final cleaning requirements.

          - Touch up paint and otherwise repair and restore marred exposed finishes to eliminate visual defects.

        - Inspection: Submit a written request for inspection to determine Substantial Completion a minimum of 10 days prior to date the Work will be completed and ready for final inspection and tests. On receipt of request, Engineer and Construction Manager will either proceed with inspection or notify Contractor of unfulfilled requirements. Engineer will prepare the Certificate of Substantial Completion after inspection or will notify Contractor of items, either on Contractor's list or additional items identified by Engineer, that must be completed or corrected before certificate will be issued.

      - FINAL COMPLETION PROCEDURES

        - Submittals Prior to Final Completion: Before requesting final inspection for determining final completion, complete the following:

          - Submit a final Application for Payment.

          - Certified List of Incomplete Items: Submit certified copy of Engineer's Substantial Completion inspection list of items to be completed or corrected (punch list), endorsed and dated by Engineer. Certified copy of the list shall state that each item has been completed or otherwise resolved for acceptance.

          - Certificate of Insurance: Submit evidence of final, continuing insurance coverage complying with insurance requirements.

          - Submit pest-control final inspection report.

        - Inspection: Submit a written request for final inspection to determine acceptance a minimum of 10 days prior to date the work will be completed and ready for final inspection and tests. On receipt of request, Engineer and Construction Manager will either proceed with inspection or notify Contractor of unfulfilled requirements. Construction Manager will prepare a final Certificate for Payment after inspection or will notify Contractor of construction that must be completed or corrected before certificate will be issued.

      - LIST OF INCOMPLETE ITEMS (PUNCH LIST)

        - Organization of List: Include name and identification of each space and area affected by construction operations for incomplete items and items needing correction including, if necessary, areas disturbed by Contractor that are outside the limits of construction.

          - Organize list corresponding to bid item.

          - Organize items applying to each bid item by major element.

          - Submit list of incomplete items in the following format:

            - PDF electronic file. Engineer, through Construction Manager, will return annotated file.

      - SUBMITTAL OF PROJECT WARRANTIES

        - Time of Submittal: Submit written warranties on request of Engineer for designated portions of the Work where warranties are indicated to commence on dates other than date of Substantial Completion, or when delay in submittal of warranties might limit Owner's rights under warranty.

        - Organize warranty documents into an orderly sequence based on the table of contents of Project Manual.

        - Warranty Electronic File: Provide warranties and bonds in PDF format. Assemble complete warranty and bond submittal package into a single electronic PDF file with bookmarks enabling navigation to each item. Provide bookmarked table of contents at beginning of document.

          - Submit on digital media acceptable to Engineer.

        - Provide additional copies of each warranty to include in operation and maintenance manuals.

- PRODUCTS

      - MATERIALS

        - Cleaning Agents: Use cleaning materials and agents recommended by manufacturer or fabricator of the surface to be cleaned. Do not use cleaning agents that are potentially hazardous to health or property or that might damage finished surfaces.

- EXECUTION

      - FINAL CLEANING

        - General: Perform final cleaning. Conduct cleaning and waste-removal operations to comply with local laws and ordinances and Federal and local environmental and antipollution regulations.

        - Cleaning: Employ experienced workers or professional cleaners for final cleaning. Clean each surface or unit to condition expected in an average commercial building cleaning and maintenance program. Comply with manufacturer's written instructions.

          - Complete the following cleaning operations before requesting inspection for certification of Substantial Completion for entire Project or for a designated portion of Project:

            - Clean Project site, yard, and grounds, in areas disturbed by construction activities, including landscape development areas, of rubbish, waste material, litter, and other foreign substances.

            - Clean exposed exterior and interior hard-surfaced finishes to a dirt-free condition, free of stains, films, and similar foreign substances, if construction activities caused the dirt, stain, or film to accumulate. Avoid disturbing natural weathering of exterior surfaces. Restore reflective surfaces to their original condition.

            - Remove debris and surface dust from limited access spaces, including roofs, plenums, shafts, trenches, equipment vaults, manholes, attics, and similar spaces.

            - Sweep concrete floors broom clean in unoccupied spaces.

            - Clean plumbing fixtures to a sanitary condition, free of stains, including stains resulting from water exposure.

            - Leave Project clean and ready for occupancy.

        - Construction Waste Disposal: Comply with waste disposal requirements in Section 015000 "Temporary Facilities and Controls" and Section 017419 "Construction Waste Management and Disposal."

      - REPAIR OF THE WORK

        - Complete repair and restoration operations, before requesting inspection for determination of Substantial Completion.

        - Repair, or remove and replace, defective construction. Repairing includes replacing defective parts, refinishing damaged surfaces, touching up with matching materials, and properly adjusting operating equipment. Where damaged or worn items cannot be repaired or restored, provide replacements. Remove and replace operating components that cannot be repaired. Restore damaged construction and permanent facilities used during construction to specified condition.

END OF SECTION 017700