## All Port Strategies 2022-2027
Port of Port Orford - Comprehensive Natural Hazard Mitigation Strategies (2022-2027)
Total Actions: 17 ¦ High Priority: 7 ¦ Medium Priority: 7 ¦ Low Priority: 3
Action ID | Title | Hazard | Estimated Cost | Timeline | Priority | Goals | Description | Partners | Funding Source
22-MH-01 | Retrofit and maintain tsunami evacuation route from port, including identifying and installing alternate route | Multi-Hazard | $2-3 Million | 2-3 years | High | 1,2,3,4,5 | Personnel visiting and working at the port will have limited tsunami evacuation routes available in the event of a large Cascadia earthquake. According to the DOGAMI Beat the Wave Report, the port is forecasted to have less than 15 minutes to evacuate before a XXL wave arrives. The 2021 Port Orford TEFIP identifies the need for landslide mitigation along Dock Road and seismic retrofitting of the road itself. The Port will also identify and install an alternate evacuation footpath north of the landslide zone along Dock Road. | City of Port Orford, Multiple County Departments, Oregon Department of Emergency Management (OEM), FEMA | County Grants, State Grants, Federal Grants
22-MH-02 | Replace, increase size and stability of, and install new dock piles | Multi-Hazard | $200k | 1-3 years | High | 1,2,3,4,5 | The current piles and locations restrict the size of boats. The piles may be compromised due to previous hazard impacts such as the 2011 tsunami, extreme waves, and severe storms. There are 37 piles which were last replaced in 2000. The piles have been repeatedly exposed to multiple hazards requiring replacement. Due to the unique dolly dock, current pile placement would not meet the needs of large ships delivering resources following disasters. The Port serves as a vital lifeline for north Curry County. | City of Port Orford | State Grants, Federal Grants
22-MH-03 | Secure funding for assessment of port dock and seismic upgrades | Multi-Hazard | $100k | 2-5 years | High | 1,2,3,4,5 | The Port has a unique high dock construction with sheet pile in place of typical pilings. The sheet pile was installed with the original dock in 2000 and may not withstand an earthquake. There has not been an assessment since installation. The sheet pile extends underwater, making thorough assessment difficult. Visual deterioration exists. Excessive shoaling requires regular dredging directly adjacent to the dock. The port has concerns about sheet pile stability due to potential undermining effects of annual dredging. A compromised dock will inhibit re-establishment after a catastrophic event. | City of Port Orford, Multiple County Departments | State Grants, Federal Grants
22-MH-04 | Ensure new infrastructure components are adequately designed to minimize risk from natural hazards | Multi-Hazard | $3 Million | 5-10 years | High | 1,2,4,5 | The aging infrastructure of port components causes concern regarding port stability and resilience. The electric facility is located at the base of an unstable bluff, at increased risk during earthquake, king tide, flooding, and tsunami events. Assessment needed for vessel hoists to withstand earthquake and tsunami. Vessel hoists require backup power generator to expedite re-establishment. The breakwater placement has resulted in excessive shoaling, requiring annual dredging. New infrastructure components should be disaster resilient to facilitate rapid port operation re-establishment. | City of Port Orford, Multiple County Departments | State Grants, Federal Grants
22-MH-05 | Relocate/reconfigure harbor control structures | Multi-Hazard | $5 Million | 5-10 years | High | 1,2,4,5 | Harbor controls will be damaged, degraded, or destroyed during a tsunami or flood event. The breakwater has been damaged multiple times, requiring repairs and negatively affecting port operations. Debris in the water poses additional risks to control structures, the dock, boats, and port facilities. Control structure relocation/reconfiguration and reinforcement is necessary to protect the port and reduce hazard impact on port operations. | City of Port Orford, Multiple County Departments, USACE | State Grants, Federal Grants
22-MH-06 | Reinforce, elevate, retrofit commercial receiving docks for resilience | Multi-Hazard | $750k | 10-15 years | Medium | 1,2,4,5 | Dock has received damage in previous high wave events. Reinforcement, elevation, and retrofitting needed for long-term resilience. | City of Port Orford | State Grants, Federal Grants
22-MH-07 | Stormwater drainage system upgrade | Multi-Hazard | $600k | 5-10 years | Medium | 1,2,4 | Antiquated system needs an upgrade to necessitate new development and improve drainage capacity. | City of Port Orford | State Grants, Federal Grants
22-MH-08 | Upland Storage Area – Aboveground fuel storage, fuel, water, wastewater, electrical service line support structure | Multi-Hazard | $15k | 5-10 years | Medium | 1,2 | Reinforcement or relocation should be considered to protect the Upland Storage area from natural hazards. | City of Port Orford | State Grants, Federal Grants
22-MH-09 | Inventory system infrastructure locations subject to flood damages, including scour/erosion | Multi-Hazard | Staff Time | 1-3 years | Medium | 1,2,4,5 | There needs to be an inventory to prioritize projects and conduct assessments following a disaster. | City of Port Orford | Staff Time
22-MH-10 | Purchase equipment/assets (boats, cranes, hoist, dozer) to assist in response and recovery activities | Multi-Hazard | $50k | 5-10 years | Medium | 1,4,5 | The port does not have equipment to store outside the tsunami inundation zone, increasing the vulnerability of the port. Equipment will be staged outside the tsunami inundation zone to expedite re-establishment of the port. | City of Port Orford, Curry County | State Grants, Federal Grants
22-MH-11 | Fortify and armor breakwaters | Multi-Hazard | $5 Million | 10-15 years | Medium | 1,2,4,5 | The breakwater has been damaged in the past. The breakwater is needed to protect the cove and dock. | City of Port Orford, USACE | State Grants, Federal Grants
22-MH-12 | Reduce exposure of petroleum/chemical facilities | Multi-Hazard | $250k | 5-10 years | Low | 1,2 | Reinforce, protect, and/or relocate facilities to prevent exposure due to natural hazards. | City of Port Orford | State Grants, Federal Grants
22-MH-13 | Install debris deflection booms to protect dock/port | Multi-Hazard | $100k | 5-10 years | Low | 1,2,4,5 | Excessive debris carried by king tides, floods, and tsunamis creates additional tasks for the port to complete before operations can re-establish. | City of Port Orford | State Grants, Federal Grants
22-EQ-01 | Evaluate the seismic vulnerabilities of embankments and over structures, prioritize replacements with seismically designed stabilizing methods | Earthquake | $20k | 2-5 years | High | 1,2,4,5 | The port is exposed to increased cascading risks in the event of a large earthquake. Graveyard Point overlooks the port, posing a risk of boulders and rocks tumbling onto the port and potentially blocking evacuation routes. The 2021 TEFIP identified a zone in need of landslide mitigation along Dock Road, and seismic retrofitting of the road itself. Dock Road is the identified tsunami evacuation route. The port and evacuation routes are at risk of liquefaction. Currently, the port facilities are not retrofitted for seismic events. | City of Port Orford, Multiple County Departments | State Grants, Federal Grants, FEMA
22-LS-01 | Embankment repair, via H-pile/concrete section stabilization | Landslide | $500k | 10-15 years | Medium | 1,2,4,5 | A landslide event will prevent port evacuation, current evacuation route will be blocked by the landslide. Landslide mitigation is necessary to protect port employees. | City of Port Orford, Curry County | State Grants, Federal Grants
22-TS-01 | Install tsunami signage and tsunami education displays | Tsunami | $10k | 1-3 years | High | 1,2,4,5 | Within the port area there is a need for tsunami zone educational signage. The port attracts many visitors due to the unique dolly dock, access to local seafood, ecotours, and coastal views. Installing tsunami educational signage decreases risk to visitors, tenants, and port employees while increasing awareness. There is a lack of tsunami evacuation route signage within the port and along the evacuation route. Additional way finder techniques will be considered to improve evacuation route identification. | City of Port Orford, Multiple County Departments | State Grants, Federal Grants

## Summary by Priority
Port of Port Orford Mitigation Strategy Summary
Priority | Count | Est. Cost Range | Actions
High Priority | 7 | $10.33M - $11.33M | 22-MH-01, 22-MH-02, 22-MH-03, 22-MH-04, 22-MH-05, 22-EQ-01, 22-TS-01
Medium Priority | 7 | $7.865M+ | 22-MH-06, 22-MH-07, 22-MH-08, 22-MH-09, 22-MH-10, 22-MH-11, 22-LS-01
Low Priority | 3 | $350K | 22-MH-12, 22-MH-13
TOTAL | 17 | $18.545M - $19.545M+ | All 17 Actions

## County Actions - Port Relevant
Curry County-Wide Actions Applicable to Port of Port Orford
Action ID | Title | Hazard | Timeline | Responsible Agency | Priority | Description | Status | Applicability to Port
22-MH-23 | Encourage special districts (including ports) to develop addenda to the Curry County Natural Hazards Mitigation Plan | Multi-Hazard | 1-3 years | Curry County Emergency Management | Medium | This action encourages special districts including ports to develop detailed addenda to the county plan, ensuring comprehensive hazard mitigation planning across all jurisdictions. | Ongoing 2016 Action #16-MH-11. Required by FEMA, supported by DLCD. | Directly encourages Port of Port Orford to maintain and enhance its hazard mitigation planning efforts